Embedding Blended Learning in a University’s Teaching Culture: Experiences and Reflections

Hugh C. Davis1 and Karen Fill2

1 Learning Technology Research Group, ECS, The University of Southampton, Southampton, UK

2 Learning and Teaching Enhancement Unit, The University of Southampton, 
Southampton, UK

hcd@ecs.soton.ac.uk, k.e.fill@soton.ac.uk

Abstract. Blended learning is a methodology with the power to transform the student experience by combining traditional face-to-face teaching methods with authentic on-line learning activities in a more student-centred approach. In spite of these advantages, university teachers find it difficult to adopt these new techniques as institutional practices are geared to support more traditional approaches. In this paper we describe how a project, funded to support international collaborations, has allowed a university to explore models for change and we examine issues concerned with sustaining the work of the project after the funding is completed.

Keywords: Blended Learning; Institutional Change; e-learning.

1   Introduction

The DialogPLUS project is a collaboration between Penn State University, the University of Leeds, UCSB, and the University of Southampton which began in February 2003 to investigate ‘Digital Libraries in Support of Innovative Approaches to Teaching and Learning in Geography’. It was funded for three years by the Joint Information Systems Committee (JISC) in the UK and the National Science Foundation (NSF) in the USA under the Digital Libraries in the Classroom Programme.  According to JISC

“This programme aims to examine how integrating recent technical developments with digital content will improve the learning experience of students and provide new models for the classroom including the impact of integration on student achievement, retention, recruitment and on institutional structures and practices.

Specific objectives are to:

- Bring emerging technologies and available digital content into core teaching and learning

- Develop and use innovative approaches in integrating technologies for the benefit of undergraduate teaching

- Demonstrate how the pedagogical process needs to be adapted or developed to support the learning process when using technology

- Examine the human and organisational issues associated with implementing new modes of teaching.”

Martin & Treves (2006) and Durham (2006) have described aspects of this project from the standpoint of geographers involved in the project, and these papers address the first three bullet points above in some detail. At the University of Southampton, as well as geographers, the team included learning technologists, from the School of Electronics and Computer Science and educational researchers from the School of Education. This paper examines their role and the effect the project has had on the institution as a whole.

A primary objective of the DialogPLUS project was to investigate the practicalities of the joint design and sharing of learning activities, based upon existing digital resources. JISC and the NSF have already funded the production and licensing of many digital resources for use in education and research, and this programme was very much concerned with deploying such resources in blended learning, exploring the associated technical, educational and organisational issues, and evaluating the impact on students and staff.

2	Developing the Project

An important starting point for the leaders of DialogPLUS was that the project should be pedagogically, rather than technically, led, and that the teachers should have ownership of the way it developed.

To this end, the first task was to put the geographers in charge and to give them the independence to work in a way that suited them. At both Leeds and Southampton we were able to use the funding to employ young geography lecturers who could work on the curriculum changes directly, or relieve existing teachers from some of their load in order that they could spend time redesigning their courses. In both Schools we were also able to employ some learning technologist time – at Southampton a full time appointment was made and the member of staff had an office in the School of Geography.

The next task was to identify where in the curriculum to make interventions. In many e-learning projects the initiative for the undertaking has arisen from teaching staff keen to keen to innovate and improve their teaching. While this is laudable, it is difficult for such staff to make an impression on the curriculum as a whole – typically their efforts will affect only the course or module on which they teach, and when they stop teaching the module innovations will often be lost. Changes are more likely to become embedded when they are planned as an integral part of the curriculum, and this can usually only be achieved with the active encouragement of senior management. In our project, both at Leeds and at Southampton, the Head of School of Geography was an active participant.  These team members had the influence and enthusiasm to enable their Schools to take a curriculum wide view of where the e-learning innovations would be best made, and they had the authority to alter the teaching loads of members of their staff in order to allow them to participate in this project and to develop e-learning activities.

Many e-learning innovations are situated within only one School. An advantage of this project was that there were four Universities involved, and an interesting dimension was added due to the fact that two were in the UK and two were in the USA. At our early meetings the geographers compared syllabuses and identified areas of overlap where collaboration would have most potential benefit for project members. As anyone who has worked on such collaborations will know, this process was not as straight forward as might be expected; geography is actually a composite of many subjects and different geographers have quite different views of the discipline. These differences were most apparent when comparing universities either side of the Atlantic. However, it was possible to reach some level of agreement and a partition of effort was established.

Having agreed the curriculum mapping, the next problem to confront was the issue of technical platforms. Each university used a different platform for delivering learning resources. One of the important technical objectives of this project was to identify solutions to the problem of interoperability of on-line learning activities. The authors have long experience of working with and supporting academics in producing learning materials, and have found that a good approach has been to allow the academics to specify their needs, then to show them technological solutions that might meet those requirements, rather than starting with the technology.

In DialogPLUS this approach had mixed results. From early meetings, that sought to establish common ground and a shared terminology, emerged the idea of a nugget. A nugget was defined as containing all that was needed to delineate a discrete learning activity. It should consist of

- At least one learning objective

- Instructions to students on how to carry out the activity

- The resources (or links to the resources) necessary to support students in carrying out the activity.

- Optionally, some assessment of the activity. (Successful completion of the activity itself was seen to be the sufficient in some cases)

Once the academics had satisfied themselves that nuggets were what they wished to make and exchange, the learning technologists introduced the ideas of learning objects and SCORM. The academics were encouraged to go ahead and create their nuggets and the learning technologists would take care of packaging them in accordance with some interoperable standard. The results of this approach are discussed further in the next section.

In order to support academics with the unfamiliar task of creating on-line learning activities we developed the DialogPLUS Learning Activity Toolkit (Conole and Fill, 2005) which scaffolds users through the process of designing learning activities by providing a step-by-step guide to help them make theoretically informed decisions and choose appropriate tools and resources. It also provides a database of existing learning activities and examples of good practice which can then be adapted and reused for different purposes. As part of the technical development of the toolkit, we also compared our schema and metadata with those in the emerging IMS Learning Design (Bailey et al., 2006).

Following the initial discovery stage of the project, the team moved into development mode; nuggets were developed in a range of topics, they were deployed for use by students, they were evaluated, they were improved, and work on new nuggets began. In the course of these developmental iterations it became clear that extensive sharing of resources, in the sense of each partner using the same nuggets in different courses, was not really possible or desirable. Cultural, curricular and cohort differences militated against this. Generic activities, such as one to encourage academic integrity (Fill et al, 2006), and tools, such as Penn State’s concept mapping application were taken up enthusiastically and the partners began to explore ways to share students on blended learning Masters courses.

Certainly at Southampton, by the end of the second year of the project the School of Geography was seen as a University leader in the blended learning domain and as a “mature” pocket of e-learning that could serve as a positive exemplar of how such work could develop.

3   Reflecting on the Project

An interesting aspect of the ‘maturity’ of this pocket is how dependent it may be on the stability of personnel, technology and course content. Sustainability and the associated issue of re-use of learning resources are now considered and illustrated with anonymous quotations from interviews with the geographers at the University of Southampton.

3.1 Sustainability

I think it's hard to tell how long it lasts but it's raised the temperature of teaching and learning practice here in geography and (…) because for the most part the academics round here are committed to the quality of their teaching, they will continue to take some of those things forward. (G1)

When the enthusiasm for, and recognition of the benefits of, blended learning are shared in a department or teaching team, innovations are likely to become embedded. However, as we have already seen in a small way at Southampton, when the champions retire or move on they may sometimes be replaced by staff who are not as enthused. Faced with many demands on their time and not fully briefed about why and how blended approaches have been developed, in-coming teachers may drop or reduce the online components. They may feel unable to defend the approach when questioned by colleagues or students.

Even for staff who continue to teach on the same modules and wish to carry on with blended learning, there are issues to do with updating the digital resources they have created, especially if the I.T. infrastructure changes and / or they no longer have local, timely technical support.

The currency of these materials, it seems to me, diminishes quickly. They need updating frequently to keep them fresh and working properly. So it will be very, very interesting to see how that works, whether people will be able to maintain their resources at the current high level of standard .(G2)

While academic staff in the project have developed their skills in that kind of curriculum planning, syllabus content planning, matching assessments to learning outcomes and really thinking about how e-learning and digital libraries can help, particularly in this subject, what we haven’t done of course is developed any skills whatever in the web authoring of that kind of approach. I think we’d feel quite challenged to do that ourselves; we wouldn’t want to do that ourselves because it’s time consuming. (G2)

Those who endorse the benefits of the ‘learning object economy’ (Duncan, 2004) would probably respond to these and similar concerns by advocating the re-use and re-purposing of digital learning resources created by others and made available via repositories managed on behalf of the education community. However, this aspect of e-learning is still far from mature in UK Higher Education and, in our experience, it does not address the real needs of front-line teachers.

The UK funders (JISC) of the DLIC programme were keen to ensure that the changes made as the result of this project were embedded in the teaching culture of the universities. To this end they required that the UK projects continued for two years after the three funded years; we are in that phase now. Although there is no doubt that most of the blended courses will continue for at least that period, and that the Schools will continue to develop new blended resources, we also have examples where staff have moved on, and the new teacher has not re-used the resources. We do not yet have the evidence to conclude whether this is due to the new teachers being uncomfortable with the teaching method, or whether this is simply due to the timely and appropriate evolution of taught content in a research-led teaching department.

3.2 Re-use of learning resources

As discussed elsewhere (Fill et al., 2006), whilst academics involved in the DialogPLUS project have been enthusiastic about the possibilities of adopting generic resources created by others, there are cultural, contextual and curricular barriers that appear to prevent any substantial sharing of subject specific resources.  This has also been reported by (Christiansen & Anderson, 2004; Malcolm, 2005).  However, at issue in those articles was the re-use / re-purposing of materials created by ‘distant others’, that is commercial content providers, or academic and related staff in other institutions. Whereas, our geographers are much more concerned about the lifespan of their own resources, what can be re-used, what will need to be updated year on year, and the support needed to do that for some of the technically complex online objects and activities.

The other thing is when we developed some of the nuggets we forgot the technical barriers. For example, the three ePracticals for (a specific course). I can never actually manage to see how they are working and to repurpose it. I can't see how, it's too complex. (G3)

The concern always was that when the support staff disappear the project falls off the precipice. I don’t think that’s happening. The teaching that’s been developed and other elements are slowly beginning to be rolled out. That’s continuing, but it would be a lot easier to do that if there was that kind of resource available for people to buy into, perhaps competitively. However it was arranged, it would be hugely helpful. (G2)

Depending on how technology moves, it's possible that in a few years you could have some major technological change or cultural change in the sector that overtakes the whole project, through no fault of the project at all but it’s a leading edge thing and the leading edge can change shape and change direction. Pace of change could wash away some of the long term impact I suppose. (G4)

These reservations do beg the question of whether an approach to learning and teaching partly based on current computer technology will ever be ‘mature’. It is possible that institutional strategies, underpinning the planning and implementation of the ‘efrastructure’ and the provision of timely and effective staff training, could mitigate some of the uncertainties. However, there is a cycle of innovation that results in the strategy sometimes lagging behind the work at the coal face. In the next section we discuss how the DialogPLUS project has contributed to the e-learning strategy at the University of Southampton.

4  Contribution to Institutional Strategy

The management of the University of Southampton is very much “collegial” in style; the majority of its income is distributed to the Schools, and the decisions about how to spend it are largely taken at that level. This makes it difficult to introduce top-down change as there is no single point of decision making; instead any decision must be taken by each School, and there is no guarantee that what is agreed by one School will also be agreed by another (White, 2006). Each School decides its own curriculum and is largely responsible for financing its delivery. However, by the time the University teaching budget has been divided between all the Schools, any surplus with which to fund change and innovation is usually very small, and typically the centrally retained funds are spent on e-learning software and on-line resources rather than on developing learning materials and activities.

Our problem, in this environment, has been how to assist Schools with making change, getting beyond the “PowerPoints on-line” instantiation of e-learning to adopting a small, but appropriate amount of blended learning. The DialogPLUS project has provided us with a good model for this. In the School of Geography we observed that change was successful, and more embedded than we have seen in previous projects, when the School leadership took a pro-active approach in facilitating curriculum change, enabling appropriate staffing of curriculum development teams. This change was aided by the project funding which, once divided between partners, was relatively modest. The University of Southampton is a research-led institution and its academics are often motivated by bidding for grants and carrying out projects; we suggest that this model of local leaders introducing change is much more effective in this type of culture than exhortations from the centre to change.

We are currently investigating the possibility of establishing a strategic fund within the University which will enable Schools to bid for assistance in introducing blended learning in a curriculum wide approach. The assistance will generally come in the form of teaching staff and learning technologists (based in their Schools), and bidders will be very much encouraged to work with other partners or consortia.

5. Conclusions: Critical Success Factors – and Failures

The DialogPLUS project has had a number of useful outcomes. We have produced some excellent learning activity nuggets, which are now being loaded into JORUM. We have produced the Toolkit, a kind of pedagogical planner, and we gained useful understanding of the problems of sharing and re-use through our work on the generic academic integrity nugget (Fill et al., 2006) and on co-operative design through our work on the GPS activities (Durham & Arrell, 2006).

However, most importantly the experiences of carrying out the DialogPLUS project have enabled us to identify a number of critical factors which we believe have been important in ensuring success in embedding the changes that the project funded.

5.1 Active Involvement of Senior Management.

Many readers will be familiar with the letters of support that funding bodies require Senior Management to produce to indicate institutional commitment to some particular project. Often this institutional commitment is, in reality, little more than agreeing to allow the project to go ahead without overheads.

In the DialogPLUS project, at the UK end we had the Head of the Schools of Geography (at Southampton and Leeds), the Head of the Learning Technology Research Group and the Professor of Educational Innovation in Post-Compulsory Education at Southampton as active managers in the project (indeed the latter two became responsible for e-Learning Strategy across the University during the course of the project). It would be difficult to overestimate the influence these four people were able to have on their colleagues, the School curriculum and the University Strategy.

5.2 The Whole Curriculum Approach

This approach suggests that rather than changing a single module within a programme to include blended learning, it is better to undertake an entire curriculum review, and to identify suitable places to include blended activities. Of course, the selection will not only be dictated by the appropriateness of the learning outcomes, but also by the availability of suitable teaching staff and other constraints such as timetabling and room allocation. In many ways we see this approach to the inclusion of blended learning as being similar to that of generic key skills; it is much improved by a curriculum wide process, rather than doing it all in a single module, often out of context. Undoubtedly, taking such an approach requires the active participation of senior management.

An interesting observation from our colleagues at Penn State University, who have been involved far longer in e-learning (at a distance), is that it is useful to consider what is the “right amount” of e-learning to offer in a curriculum; too little and we are not helping student to learn appropriate life-long learning skills, but too much, and the students will start to complain that they had not signed up for a virtual degree, and that they want more face-to face opportunities. Our evaluation activities also indicate that both staff and students find they spend more time on the e-learning components of blended modules than the traditional elements (Fill, 2006b).

5.3 Funding

The DialogPLUS project would not have happened without external funding. Although we had Schools of Geography that were ready to change, they simply did not have the funds to take the risky steps required to bring about a transformation. The funding was necessary to employ extra teaching staff, either to produce and tutor blended activities themselves, or better still, to release existing staff from their teaching in order to spend time preparing blended activities. Post funding, the Schools now continue to employ some of the staff hired originally just for the project.

5.4 Support at the Point of Need

Teachers, and their academic Schools need support when they want it! In many universities support for e-learning is a central service, and however willing the staff may be, they will have multiple conflicting undertakings. Putting a dedicated learning technologist into the School of Geography at Southampton was highly influential. This member of staff was always available to help when needed, and furthermore was able to sit down with academics and show them individually what was possible. It is well established that an effective approach to group change is to introduce a change agent (see for example Havelock & Zlotolow, 1995). A communicative learning technologist can be a very good change agent.

5.5 Collaborations

In a collaborative project we might have expected to share development effort and to re-use each other’s activities. This happened to a certain extent, but the benefit of the collaborations turned out to be more subtle than we had anticipated. When a team is undertaking change, they will experience many moments of self doubt and loss of confidence. Working with colleagues from other Schools and Universities that we respected helped the team to achieve coherence and gain self confidence to cope with and move through the bad spots, and provided a common sense of purpose. The close relationships developed in occasional face-to-face meetings have formed a sound basis of understanding for our monthly virtual meetings using Access Grid and other virtual conferencing tools.

5.6 Some of the things that did not work

Not everything in the DialogPLUS project worked perfectly, and it is useful to reflect on our failures as well as our successes.

The project results were more significant for the UK partners than for the US partners. There are probably multiple reasons for this.  In the USA the DialogPLUS undertakings were conceived much more as research, rather than development, projects, as in the UK. This had two disadvantages; the first being that the US participants did not have the senior management and curriculum buy-in that we had in the UK, and the second that their funding was subject to overheads, such that they had significantly less funding than the UK partners. Furthermore, the UCSB contribution had been expected to be based around the use of the Alexandria Digital Library (ADL), an NSF funded library of geo-referenced digital images and other resources. During the timescale of this project the NSF funding of this resource diminished,  possibly as tools such as Google Earth provided some of their important functionality, and the role that we initially envisaged for ADL never materialised.

Sharing of learning activities was not as widespread as expected. This was in part due to our failure to agree exactly what a nugget was. Learning Object specialists would suggest that important features of well designed learning objects are low coupling and high coherence (Boyle, 2003) in order to provide context independent units. But some of our learning activities were far too dependent on each other and their context of use to be shareable. We believe this problem was attributable more to the cultural issues than technical issues (Fill 2006a). We found that sometimes staff would rather encourage their students to take someone else’s module rather than try to use someone else’s materials in their own module.

Finally, it is interesting to reflect on the extent to which the practices we have developed have become embedded in use. While we are happy that we have more than adequately met the requirements of the funders to embed the use of the materials we have created, true embedding will only have happened when the introduction or creation of new blended learning materials is in balance with the wastage of unloved or out-of-date materials, and this must happen within the stable, internally funded economy of the unit of teaching. It will take longer than two years to measure this result. So watch this space!

Acknowledgements

The authors wish to acknowledge the funding bodies, JISC and NSF, and in particular the sympathetic and insightful support of Susan Eales, JISC Programme Manager for the Digital Libraries in the Classroom initiative during the developmental years of the DialogPLUS project; Professor Gràinne Conole, now at the UK’s Open University, who was the driving force behind the design of the Learning Activity Toolkit; and all the DialogPLUS geographers and learning technologists who have worked so collaboratively and untiringly to adopt blended learning practices, to source or create digital resources to improve student learning, and to evaluate and improve the innovations.

References

Bailey, C., Zalfan, M. T, Davis, H. C., Fill, K., & Conole, G. (2006). Panning for Gold: Designing Pedagogically inspired Learning Nuggets. Educational Technology & Society, 9 (1), 113-122.  [http://www.ifets.info/others/abstract.php?art_id=606]

Boyle, T. (2003). Design principles for authoring dynamic, reusable learning objects. Australian Journal of Educational Technology, 19(1), 46-58. [http://www.ascilite.org.au/ajet/ajet19/boyle.html]

Christiansen, J and Anderson, T (2004). Feasibility of Course Development Based on Learning Objects: Research Analysis of Three Case Studies, Instructional Technology & Distance Learning, 2004, 1,3. [http://www.itdl.org/Journal/Mar_04/article02.htm]

Conole, G. and Fill, K. (2005). A learning design toolkit to create pedagogically effective learning activities. Journal of Interactive Media in Education (Advances in Learning Design. Special Issue, eds. Colin Tattersall, Rob Koper), 2005/01. [http://jime.open.ac.uk/2005/08/ ]

Duncan, C. (2004). Learning Object Economies: Barriers and Drivers.      [www.elearninternational.co.uk/2004/test/2004/ref_papers/duncan_elearn2004.doc]

Durham, H and Arrell, K. (2006). GPS: the collaborative way to knowing your location. In Davis, H.C and Eales, S.M. (eds). The Proceedings of Critical Success Factors for Institutional Change (CSFIC 2006) available from http://www.csfic.ecs.soton.ac.uk/

Fill, K. (2006a) Refreshed and Reflective: The Impact of an eLearning Project on University Teachers. Proceedings of  the First International Conference on eLearning, Montreal, Canada, 22-23 June 2006. [http://www.academic-conferences.org/icel/icel-proceedings/ proceedings-icel06.htm]

Fill, K. (2006b) Quality versus time: a rationale for blended learning? Paper presented at the British Educational Research Association Conference, Warwick, UK, Sep 6-9 2006. [http://www.leeds.ac.uk/educol/documents/157113.htm]

Fill, K., Leung, S., DiBiase, D. and Nelson, A. (2006) Repurposing a learning activity on academic integrity: the experience of three universities. Journal of Interactive Media in Education, 2006/01. [http://jime.open.ac.uk/2006/01/]

Havelock, R., & Zlotolow, S. (1995). "The change agent's guide," (2nd ed.). Englewood Cliffs, NJ: Educational Technology Publications

Malcolm, M. (2005) The exercise of the object: issues in resource reusability and reuse. British Journal of Educational Technology, Volume 36, Number 1, January 2005, pp. 33-41(9)

Martin, D.J and Treves, R (2006) DialogPLUS: embedding eLearning in Geographical practice. In Davis, H.C and Eales, S.M. (eds). The Proceedings of Critical Success Factors for Institutional Change (CSFIC 2006) available from http://www.csfic.ecs.soton.ac.uk/

White, S. (2006) Critical Success Factors for Institutional Change: Some Organisational Perspectives. In Davis, H.C and Eales, S.M. (eds). The Proceedings of Critical Success Factors for Institutional Change (CSFIC 2006) available from http://www.csfic.ecs.soton.ac.uk/

# Footnotes

DialogPLUS http://www.dialogplus.org

DLIC http://www.jisc.ac.uk/index.cfm?name=programme_dlitc

SCORM http://www.adlnet.gov/scorm/index.cfm

http://www.nettle.soton.ac.uk/toolkit/userarea/default.aspx

IMS LD http://www.imsglobal.org/learningdesign/index.html

ConceptVista (www.geovista.psu.edu/Conceptvista)

Different interviewees are indicated by (G1), (G2) etc.

http://www.jorum.ac.uk/