## Action Minutes from e3an project team meeting 3 Portsmouth 7th July 2000.

Present: David Long, Djameel Azzi, Hugh Davis, Peter Ashburn, Richard Crowder, Sean Wellington, Su White, Tim Morgan David Arrell attended at lunchtime

Apologies: Jim Roach

| Item |  |  | Action | Responsibility |  |
| --- | --- | --- | --- | --- | --- |
| ## 1 |  | ## Meetings |  |  |  |
| 1.1 |  | Site meetings: Each partner to arrange meeting with steering group representative and any other relevant people at their institution. Meetings to be scheduled for August/September |  |  | All |
| 1.2 |  | Next project meeting (ptm3) : 8th September 2000 Southampton Institute Room A302 10.00 -14.00 |  |  | All |
| 1.3 |  | Ptm3 domestic arrangements to be organised by Sean Wellington, Su White to draw up agenda/timetable in collaboration with Sean |  |  | Sean/ Su |
| 1.4 |  | Project steering group meeting to be scheduled for September, after project meeting |  |  | Su |
| ## 2 |  | ## Project Admin |  |  |  |
| 2.1 |  | Project name: Agreed to go ahead with the project name as e3an. Paperwork to reflect this change |  |  | Su |
| 2.2 |  | Hugh and Su to get range of possible logo's for consideration at next meeting |  |  | Su/ Hugh |
| 2.3 |  | Su to meet with Tim Chown to fill in UKERNA forms for e3an.ac.uk |  |  | Su |
| 2.4 |  | Hugh to ensure that e3an or E3AN will work on ecs.soton.ac.uk address |  |  | Hugh |
| 2.5 |  | Staffing: Agreed to delay advertising for RA, although project team members to seek out possible suitable applicants. Meanwhile cash for technical and administrative jobs to be used on ad hoc basis, with project group agreement. |  |  | All |
| 2.6 |  | Su to brief Sandie on baseline audit etc, and to get quote on price for job |  |  | Su |
| 2.7 |  | Contacts: Each academic team member to provide contact list of known hod's and personal contacts with details of specialisms. This information is needed by Sandie |  |  | All |
| 2.8 |  | The purpose of this action to help populate database with high quality data. |  |  | Action ASAP |
| 2.9 |  | Draft Collaborative agreement to be drawn up for (Su August) circulation and discussion at next project meeting (All September) |  |  | Su/ All |
| 2.10 |  | Institutional partners to claim cash by quarterly invoice |  |  | Institutional partners |
| 2.11 |  | Project plan to be drawn up in greater detail for next project meeting (September) |  |  | Su/Hugh |
| 2.12 |  | Finances to be revisited with view to identifying larger amount of money for consultants' budget. Proposals to be brought to next project group meeting (September) |  |  | Su/ Hugh |
|  |  | ## Themes |  |  |  |
| 3.1 |  | Theme leaders to draft proposals for running their themes to be brought to next project group meeting. Theme allocation as follows: |  |  | David/ Tim/ Peter/ Sean/ Richard |
|  | David Long - Bournemouth - Analogue electronics |  |  |  |  |
|  | Tim Morgan/Djameel Azzi - Portsmouth - Digital and micro processors |  |  |  |  |
|  | Peter Ashburn - Southampton - Circuit Theory |  |  |  |  |
|  | Sean Wellington - Southampton Institute - Signal Processing |  |  |  |  |
|  | Richard to provide electrical input to each theme ;-) |  |  |  |  |
| 3.2 | Each academic team member to get copies of syllabus for theme leader, plus exam papers by the beginning of August. This information to be sent to Su who will circulate it on to each theme leader |  |  |  | All |
| 3.3 | Hugh to work through attributes for presentation at next project group meeting |  |  |  | Hugh |
| 3.4 | Hugh to get Jodi to work through some of the interoperability issues associated with different data types needed for question content |  |  |  | Hugh/Jodi |
| 3.5 | Su to work through notes from discussion on approach - to bring to next project group meeting |  |  |  | Su |
|  | ## Training & Development |  |  |  |  |
| 4.1 | Academic team members to consider applying for project management and working with your LTSN development days run by National Co-ordination team. Booking details are online. http://www.ncteam.ac.uk/events/ |  |  |  | All |
| 4.2 | Su and Hugh to see if it is possible to combine project group meeting with objective test development. Otherwise schedule ASAP. |  |  |  | Su/ Hugh |
| 4.3 | Su/Jodi to talk with Neil Sclater from the Scottish Computer Assisted Assessment Network people re collaborations on interoperability |  |  |  | Su |
|  | ## Information |  |  |  |  |
| 5.1 | Su to circulate latest benchmarking standards from QAA |  |  |  | Su |

## For Information: Theme Overview

| Theme | Theme Leader | Expertise |
| --- | --- | --- |
| Analogue electronics | David | Djameel, Sean, |
| Digital and micro processors | Tim and Djameel | David, Sean |
| Circuit Theory | Peter Ashburn | David, Djameel, Sean |
| Signal Processing | Sean |  |
| Power Electronics | Phase 2 - to be agreed | Richard |
| Electromagnetism | Phase 2 - to be agreed | Richard |
| Computer Programming | Phase 2 - to be agreed | Hugh Sean, Tim |
| Control Engineering | Phase 2 - to be agreed | Djameel |
| Maths | Phase 2 - to be agreed |  |
| Telecomms | Phase 2 - to be agreed |  |
| Datacomms | Phase 2 - to be agreed |  |
| Physics/Semi conductors | Phase 2 - to be agreed | Peter |

NB: Richard to provide electrical input to all phase 1 themes :-)