## Action minutes from e3an project team meeting 4 Bournemouth University 13th October 2000.

Present: Dave Long, Djamel Azzi, Jim Roach, Peter Ashburn, Richard Crowder, Su White, Tim Morgan

Apologies: Hugh Davis, Sean Wellington

| Item |  |  | Action | Responsibility |  |
| --- | --- | --- | --- | --- | --- |
| ## 1 |  | ## Meetings |  |  |  |
| 1.1 |  | Site meetings. Bournemouth and Portsmouth to arrange dates |  |  | Dave, Tim |
| 1.2 |  | Next project meeting (ptm5) : 3 November 2000 Southampton University, Zepler Building 10.00-14.00 |  |  | All |
| 1.3 |  | Ptm5 domestic arrangements to be organised by Su White. |  |  | Su |
| 1.4 |  | Project steering group meeting be scheduled October 16th, members to attend if possible |  |  | All |
| 1.4 |  | Evaluator meetings to be scheduled on 16th and 17th |  |  | All |
| ## 2 |  | ## Project Admin |  |  |  |
| 2.1 |  | Hugh to scan logo's, put onto web page, and circulate url - voting to follow :-) |  |  | Hugh, All |
| 2.2 |  | Su fill in UKERNA forms for e3an.ac.uk, pass to Tim Chown |  |  | Su |
| 2.3 |  | Draft Collaborative agreement to be modified and taken to steering group meeting for discussion |  |  | Su |
| 2.4 |  | Institutional partners to claim cash by quarterly invoice |  |  | Institutional partners |
| 2.5 |  | Revised project plan to be taken to steering group, circulated to team, then forwarded to NCTeam |  |  | Su |
| 2.6 |  | Detail of finances to be taken to steering group meeting |  |  | Su |
| ## 3 |  | ## Themes |  |  |  |
| 3.1 |  | Details of collaborating consultants to be passed to relevant theme leaders from their own institutions, copied to Su please |  |  | All |
| 3.2 | Su to email consultants with workshop details asking for confirmation of attendance dates. Info to go on spreadsheet on web pages |  |  |  | Su |
| 3.3 | Su to collate and circulate copies of syllabus |  |  |  | Su |
| 3.4 | Su to work on paper version of question templates for next meeting |  |  |  | Su |
| 3.5 | Hugh to update question templates for next meeting |  |  |  | Hugh |
| 3.6 | Hugh to update workshop plan next meeting, incorporating discussion points from meeting. |  |  |  | Hugh/Su |
| 3.7 | All to bring two sample questions to next meeting. One short question and answer in the style of the question which peter brought to last meeting. One exam style question, both of which can be used as exemplars during the training day. |  |  |  | Richard, Sean, Tim, Djamel, Tim, Jim, Dave |
| ## 4 | ## Information |  |  |  |  |
|  | Su to contact Julie Barratt on press releases etc |  |  |  | Su |
|  | Su to draft and circulate press release |  |  |  | Su |
| ## 5 | ## Planning |  |  |  |  |
|  | Draft job descriptions for RA post to be considered at November Meeting |  |  |  | Su |
|  | Researcher to begin work in January |  |  |  |  |
|  | Proof of concept demo of database for Easter |  |  |  |  |
|  | Some kind of launch meeting for community at Easter (? Timing to fit with engineering conference?) |  |  |  |  |